## Sheet1
Count of Vendor | Column Labels
Row Labels | Completed | Hold | Pending | TBD | WIP | Grand Total
SEP | 1 |  | 1 |  | 3 | 5
Firewall Cisco | 1 |  |  |  | 1 | 2
Malwarebytes | 4 |  |  | 2 | 3 | 9
Mimecast | 1 |  |  |  |  | 1
Rapid 7 |  |  |  |  | 1 | 1
SecureWorks | 2 |  |  |  |  | 2
Zscaler | 3 | 1 | 2 | 3 | 2 | 11
Zscaler / CISO/Mimecast |  |  |  |  | 1 | 1
Grand Total | 12 | 1 | 3 | 5 | 11 | 32

## Vendor & CSI
Vendor | Meeting date | Clarifications | Owner | Category | Is this part of CSI | Proactive / Reactive | Status | Comments
Malwarebytes | 2018-07-04 | Downloading the threat details are slow in console | Senthil Kumar | Clean-up activity | No | NA | Completed | Working with MB team, need to do DB clean-up / upgrade MBMC from 1.7 to 1.8 #00063909 - MBMC: Freezing - CHG0029586
Malwarebytes | 2018-07-04 | Category / threat / Sev vector wise list | Mahesh | Alert | Yes | Proactive | WIP | Pending with SecureWorks
Malwarebytes | 2018-07-04 | threshold need to set for the alert | Mahesh | Alert | Yes | Proactive | WIP | Pending with SecureWorks
Malwarebytes | 2018-07-04 | Weekly / Monthly Report | Sathya | Report | Yes | Proactive | WIP | Jean requires Powershell / Python access to MB Console - Need to work with MB Support team
Malwarebytes | 2018-07-04 | MB console issue, during the DB is down | Senthil Kumar | Incident | No | NA | NA | Need discuss during the technical meeting
Malwarebytes | 2018-07-04 | Database size is 3.1 GB need to be cleaned up | Senthil Kumar | Clean-up activity | No | NA | Completed | CHG0029586
Zscaler | 2018-07-11 | Torrent site category block | Mahesh | Block | Yes | Reactive | Completed | CHG0029598
Zscaler | 2018-07-11 | Zscaler FW Logging apart from 80/443 other services need to be logged / details need to checked with Zscaler | Mahesh | Logging | Yes | Proactive | TBD | Subscription -TBD
Firewall Cisco | 2018-07-11 | Cisco FW audit report findings using the Nipper studio | Mahesh | Report | Yes | Proactive | Completed | Audit completed, Findings shared, need to work with BT with findings
SecureWorks | 2018-07-11 | Repeated threat / alert count for that month / quarter need to be part of the incident | Darshan | Alert | Yes | Reactive | Completed | Type "0" Alert fine tuned - CR - CHG0029650
Malwarebytes | 2018-07-25 | Write policy to stop PUP.OptionalHomePagecontrol Alerts | Sathya | Alert | Yes | Reactive | Completed
SecureWorks | Aug 1st | MPLE rule to alert on broad & port scan | Sathya | Alert | Yes | Proactive | Completed
Mimecast | Aug 1st | Hash file submitting | Sathya | Activity | Yes | Proactive | Completed | CHG0029786
Firewall Cisco | Aug 1st | Discussion with BT on the FW audit findings | Mahesh | Report | Yes | Proactive | WIP | First level discussion completed, Need to work with network team and BT
Zscaler | Aug 1st | Mobile Insights | Mahesh | Block | Yes | Proactive | Hold | Data shared with George & Senthil meeting need to secheduled on 22nd Aug
Zscaler | Aug 1st | Web Spam & Anonymizer block | Mahesh | Block | Yes | Proactive | Completed | Web Spam blocked - CHG0029598
Zscaler | Aug 1st | Elevated Internet Access group | Mahesh | Report | Yes | Proactive | Pending | This will be part be Zscaler Phase III
Zscaler | Aug 17th | Advanced Threats Policy | Mahesh | Block | Yes | Proactive | WIP | Rating need be changed from 35 from 32, Working with Zscaler
Zscaler | Aug 17th | Browser Blocking | Mahesh | Block | Yes | Proactive | TBD | Need to discuss this with George
Zscaler | Aug 17th | Key word block | Mahesh | Block | Yes | Proactive | TBD | Need to discuss this with Zscaler
SEP | Aug 17th | Tor blocks / Brower block in SEP | Darshan | Block | Yes | Proactive | Pending | Tested and will be part of SEP 14 policy both server and workstation
Zscaler | Aug 17th | Cloud App Control Policy | Mahesh | Block | Yes | Proactive | WIP | Shared details with Senthil & George need to discuss
Zscaler | Aug 17th | Untrusted Server Certificates | Mahesh | Block | Yes | Proactive | Pending
Zscaler | Aug 17th | Blocked Malicious Urls .xyz | Mahesh | Block | Yes | Proactive | Completed | CHG0030570
Malwarebytes | 2018-08-21 | Block RAT Hashes | Sathya | Block | Yes | Proactive | Completed | CHG0030489
Malwarebytes | 2018-08-14 | Malwarebytes Console Upgrade | Sathya | Incident | Yes | Proactive | Completed | CHG0030915_Upgrade to 1.8.3476 is complete on Sep 16th
Rapid 7 | 2018-08-31 | Fine tune Audit Reports | Sathya / Ed | Report | Yes | Proactive | WIP | Working on fine tuning Audit reports_will be completed on or before 20th Sep
SEP | 2018-08-06 | Exe Files for Lokibot blocked in SEP | Darshan | Block | Yes | Reactive | Completed | The Lokibot Exe files set to block in SEP, CHG002995
Malwarebytes | 2018-08-27 | PUP.OptionalMindspark | Sathya | Alert | Yes | Reactive | WIP | INC790068_List of Mindspark addons sent to Team and awaiting suggestions
SEP | 2018-08-31 | Malicious application Hash from Zscaler To be added in SEP | Darshan | Block | Yes | Proactive | Completed | Total count 274 malicious hash values from Zscaler will be blocked in SEP. Naveen will workon this activity
SEP | 2018-08-31 | Identify Malicious Hash Allowed in Zscaler - Monthly | Mahesh | Block | Yes | Proactive | Completed | Total count 274 malicious hash values from Zscaler will be blocked in SEP.
SEP | 2018-08-31 | Top 10 Most Abused Top Level Domains | Mahesh | Block | Yes | Proactive | Pending | Need to block after getting approved from Geroge & Senthil
Firewall /Mimecast | 2018-09-11 | Trickbot delivered Fake Email & Phishing | Mahesh | Block | Yes | Proactive | Completed | CHG0030965
MB / SEP/ Mimecast | 2018-09-09 | Ryuk Ransomware Hash | Sathya | Block | Yes | Proactive | Completed | CHG0030824
Zscaler | 2018-09-04 | Block Top Torrent sites | Sathya | Block | Yes | Proactive | WIP | CHG0030826_Block Top 10 Torrent sites for September 2018
MB / SEP/ Mimecast / Zscaler | 2018-09-14 | Block New PyLocky_Ransomware Hashes and URLs | Sathya | Block | Yes | Proactive | WIP | CHG0031093
SEP | 2018-09-17 | Validate and exempt Chrome.exe getting blocked as a Trojan.backdoor | Sathya | Alert | Yes | Proactive | WIP | INC795947
SEP | 2018-09-20 | Save file ransomware detection in SEP | Darshan | Block | Yes | Proactive | WIP | INC796862
Zscaler | 2018-09-25 | 30000 Malicious URLS & Ips Submitted to Zscaler Blocking | Mahesh | Block | Yes | Proactive | Completed | Zscaler Case : 617123
Zscaler | 2018-09-20 | Fallout Exploit Kit Pushing the SAVEfiles Ransomware | Mahesh | Block | Yes | Proactive | Completed | CHG0031253
Zscaler | 2018-09-20 | Xbash Combines Botnet, Ransomware, Coinmining in Worm that Targets Linux and Windows | Mahesh | Block | Yes | Proactive | Completed | Zscaler Case : 617123
Zscaler | 2018-09-18 | Tomas Request to Block | Mahesh | Block | Yes | Reactive | Completed | CHG0031187
Zscaler | 2018-09-17 | URL Shorter & Redirection URLs needs to Block | Mahesh | Block | Yes | Proactive | WIP
Zscaler | 2018-09-17 | New Malware with Powerful Obfuscation Technique to Bypass Antivirus Software | Mahesh | Block | Yes | Proactive | Completed | 42716378 Symantec
ZS/IPS/Firewall | 2018-09-14 | CTU Blacklisted Domain Associated with APT Activity Detected Ips and URLS | Mahesh | Block | Yes | Reactive | Completed | CHG0031056
Zscaler | 2018-09-14 | Malicious URLS & Ips Blocked related to Phising | Mahesh | Block | Yes | Proactive | Completed | CHG0030965
Zscaler | 2018-09-10 | Intrusion Event - exploit-kit ( Cisco Source Fire ) HASH needs to be Blocked | Mahesh | Block | Yes | Proactive | WIP
Zscaler | 2018-09-26 | Hash file submitting to SEP & Malware bytes | Mahesh | Block | Yes | Proactive | WIP

## Projects
Email Security - Mimecast
SEP 14 - Novacoast
MFA - Device Authentication - Okta
Secureworks SIEM
Automation Plant Firewall
Secure On-demand Vendor Access
Zscaler phase III
Vulnerability Scanning – Rapid 7
Data Classification - Titus
PRJ0010164 | Device Authentication
PRJ0010166 | Implement SIEM Solution
PRJ0010167 | Automation Plant Network Segregation
PRJ0010176 | Symantec EndPoint Protection Version 14
PRJ0015755 | Secure On-Demand Vendor Access
PRJ0019492 | Zscaler Phase III
PRJ0019495 | Vulnerability Scanning
PRJ0020778 | Email Security

## Project Status
Project | Week 26 | Week 27 |  |  |  | Week 36
SEP 14 - Nova coast | Dev servers built and ready | Prod Servers built and ready for installation Prod policy's are download for analysis Vendor Questionnaire form completed | SEP 14 Server built and application installed,Exported policies from SEP 12 to SEP 14 ( clients un-assigned), SEP14 Managed Client package created and kept in share folder for testing. | Shared the pacjage for workstation to the Altiris team for packaging | Altiris Team created the workstation Package for the SEP 14 Client setup.Tested the package and given reviews to the Altiris team , Altiris team again creating the package based on the reviews.
SecureWorks SIEM | Add DMZ servers in SW Missing DC servers were added in SW Decomm DC servers need to be removed from SecureWorks | SIF form need to be submitted for DMZ
Automation Plant Firewall
Vulnerability Scanning – Rapid 7 |  | Prod server build completed CR in place to deploy SW Agents on Prod Server VM Policy documentation is in progress VA Scan reports uploaded to SharePoint |  |  |  | 1. VMS Policy/Procedure Document submitted for appoval 2. Conducted Assessments on BobJ Servers 3. VA Approval form created / Submitted for approval 4. R7 Engine deployed in AWS Environment, and is paired to the console 5. Sites created / Discovery enabled for all AWS Assets 6. Sites created for IFF Dev Servers 7. R7 Configuration Item has been added to Servicenow 8. PUMA Servers Scan is in progress while test PUMA Servers are being patched 9. Rapid 7 Training completed successfully 10. Fine Tuning R7 tool, Alerts, Reports in progress 11. R7 Agent deployment is to be discussed 12. Meeting scheuld on 6th Sep to discuss on Patch Management / VMS Process

## Sheet7
Tool | Completed | Hold | Pending | TBD | WIP | Grand Total
SEP | 1 |  | 1 |  | 3 | 5
Firewall Cisco | 1 |  |  |  | 1 | 2
Malwarebytes | 4 |  |  | 2 | 3 | 9
Mimecast | 1 |  |  |  |  | 1
Rapid 7 |  |  |  |  | 1 | 1
SecureWorks | 2 |  |  |  |  | 2
Zscaler | 3 | 1 | 2 | 3 | 2 | 11
Firewall & Mimecast |  |  |  |  | 1 | 1
Grand Total | 12 | 1 | 3 | 5 | 11 | 32
Technology | Proactive | Reactive | Grand Total
SEP | 4 | 1 | 5
Firewall Cisco | 2 |  | 2
Malwarebytes | 5 | 1 | 9
Mimecast | 1 |  | 1
Rapid 7 |  | 1 | 1
SecureWorks | 1 | 1 | 2
Zscaler | 10 | 1 | 11
Firewall & Mimecast | 1 |  | 1
Technology | Completed | Hold | Pending | TBD | WIP
SEP | 1 |  | 1 |  | 3
Firewall Cisco | 1 |  |  |  | 1
Malwarebytes | 4 |  |  | 2 | 3
Mimecast | 1
Rapid 7 |  |  |  |  | 1
SecureWorks | 2
Zscaler | 3 | 1 | 2 | 3 | 2
Firewall & Mimecast |  |  |  |  | 1

## Sheet6
Count of Status | Column Labels
Row Labels | Completed | Hold | Pending | TBD | WIP | (blank) | Grand Total
SEP | 1 |  | 1 |  | 3 |  | 5
Firewall Cisco | 1 |  |  |  | 1 |  | 2
Malwarebytes | 4 |  |  | 2 | 3 |  | 9
Mimecast | 1 | [5 empty] | 1
Rapid 7 |  |  |  |  | 1 |  | 1
SecureWorks | 2 | [5 empty] | 2
Zscaler | 3 | 1 | 2 | 3 | 2 |  | 11
(blank)
Grand Total | 12 | 1 | 3 | 5 | 10 |  | 31